## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
Register | Register account | Medium | Iteration 1 | DE150387 | Nguyễn Huỳnh Thắng | Iteration 1
Login | Log in to system | Simple | Iteration 1 | DE150387 | Ngô Quang Tín | Iteration 1
Logout | Log out of system | Simple | Iteration 1 | DE150387 | Ngô Quang Tín | Iteration 1
ViewUserInfo | View user's information | Simple | Iteration 1 | DE150071 | Nguyễn Huỳnh Thắng | Iteration 2
ViewNewFeed | View new feed | Medium | Iteration 1 | DE160018 | Ngô Quang Tín | Iteration 2
ViewUserPage | View user's page | Simple | Iteration 1 | DE150071 | Huỳnh Bá Phú | Iteration 2
ViewDatingPage | View dating page | Simple | Iteration 1 | DE150206 | Nguyễn Huỳnh Thắng | Iteration 2
ViewDatingProfile | View dating user's information | Simple | Iteration 1 | DE150206 | Huỳnh Bá Phú | Iteration 2
EditProfile | Edit user's information | Medium | Iteration 1 | DE160018 | Ngô Quang Tín | Iteration 2
Post | Post to timeline | Medium | Iteration 1 | DE160018 | Ngô Quang Tín | Iteration 2
EdiPost | Edit post | Medium | Iteration 2 | DE160018 | Ngô Quang Tín | Iteration 2
DeletePost | Delete post | Simple | Iteration 2 | DE160018 | Ngô Quang Tín | Iteration 2
HidePost | Hide post | Simple | Iteration 2 | DE160018 | Ngô Quang Tín | Iteration 3
ViewUserPhotos | View user's photos | Simple | Iteration 2 | DE150071 | Vương Công Dũng
ViewUserVideos | View user's videos | Simple | Iteration 2 | DE150071 | Vương Công Dũng
FriendRequest | Send friend request to other users | Medium | Iteration 2 | DE160018 | Ngô Quang Tín | Iteration 2
ListFriendRequest | View user's friend request list | Simple | Iteration 2 | DE160018 | Nguyễn Huỳnh Thắng | Iteration 2
ViewUserFriend | View user's friend list | Simple | Iteration 2 | DE150071 | Vương Công Dũng | Iteration 3
Comment | Comment on the post | Medium | Iteration 2 | DE150071 | Vương Công Dũng | Iteration 3
DeleteComment | Delete comment | Simple | Iteration 2 | DE150071 | Vương Công Dũng | Iteration 3
BlockComment | Block comment | Simple | Iteration 2 | DE150071 | Vương Công Dũng | Iteration 3
Like | Like or unlike post | Medium | Iteration 2 | DE150387 | Ngô Quang Tín | Iteration 3
ChangePassword | Change user password | Simple | Iteration 2 | DE150387 | Nguyễn Huỳnh Thắng | Iteration 2
RetrieveForgottenPassword | Retrieve forgotten password | Medium | Iteration 2 | DE150387 | Nguyễn Huỳnh Thắng | Iteration 2
BlockUserAccount | Block user's account | Simple | Iteration 2 | DE160018 | Ngô Quang Tín
DeleteUserAccount | Delete user's account | Simple | Iteration 2 | DE160018 | Ngô Quang Tín
SearchUser | Search other users | Simple | Iteration 2 | DE150071 | Vương Công Dũng | Iteration 2
ViewChatPage | View user's chat page | Complex | Iteration 2 | DE150387 | Nguyễn Huỳnh Thắng | Iteration 2
Chatting | Chat with other users | Complex | Iteration 2 | DE150387 | Nguyễn Huỳnh Thắng | Iteration 3
ViewDatingDetail | View dating detail | Simple | Iteration 2 | DE150206 | Huỳnh Bá Phú | Iteration 2
SearchDatingUser | Search dating user | Simple | Iteration 2 | DE150206 | Huỳnh Bá Phú | Iteration 2
ChangeDatingInfo | Change dating profile | Medium | Iteration 2 | DE150206 | Huỳnh Bá Phú | Iteration 2
ViewStatisticPage | View page statistics | Medium | Iteration 2 | DE150206 | Huỳnh Bá Phú
ListReportedPost | View reported posts | Simple | Iteration 3 | DE150071 | Vương Công Dũng
DeleteChatBox | Delete chat box | Medium | Iteration 3 | DE150387 | Nguyễn Huỳnh Thắng
HideChatBox | Hide chat box | Medium | Iteration 3 | DE150387 | Nguyễn Huỳnh Thắng
ReactToTarget | React other dating users | Medium | Iteration 3 | DE150206 | Huỳnh Bá Phú | Iteration 3
ListMatchTarget | View match target list | Simple | Iteration 3 | DE150206 | Huỳnh Bá Phú | Iteration 3
HideTarget | Hide other dating users | Simple | Iteration 3 | DE150206 | Huỳnh Bá Phú
BlockChatUser | Block chat user | Medium | Iteration 3 | DE150387 | Nguyễn Huỳnh Thắng
TurnOffChatNotification | Turn off chat notification | Medium | Iteration 3 | DE150387 | Nguyễn Huỳnh Thắng
LoginWithGoogle | Login with Google | Complex | Iteration 3 | DE150071 | Vương Công Dũng
UserNotification | Send notification for user | Medium | Iteration 3 | DE150387 | Nguyễn Huỳnh Thắng | Iteration 3
ViewNotification | View user's notifications | Medium | Iteration 3 | DE150071 | Vương Công Dũng | Iteration 3
UserStatus | Display user's status (online, offline,…) | Simple | Iteration 3 | DE160018 | Ngô Quang Tín
ChatStatus | Display chat status (read or not) | Medium | Iteration 3 | DE160018 | Ngô Quang Tín | Iteration 3